## Sprints
Sprint | Goal | Plan sections | Timebox (min) | Tasks | Tasks done | Status | Completed on | Commit | Notes
S0 | Repo, plan and tracker | PLAN.md | 10 |  |  | Done | 2026-10-31 | 3bc9253
S1 | Scaffold: Next.js, DB schema, triggers, policy, utilities | §2, §3, §5.1 | 20 |  |  | Done | 2026-10-31 | f98e054 | 15 tests pass; build OK
S2 | Synthetic data generator + committed seeds 1–3 | §8 | 25 |  |  | Done | 2026-10-31 | ddd79db | Seeds 1–3: 320 customers, ~4.5k txns, ~4k logins, 124 loans, 18 truth items each; deterministic
S3 | Ingestion pipeline: parse, aliases, validation, buckets, APIs | §4, §6 | 25 |  |  | Done | 2026-10-31 | eba6588 | 23 tests pass; API smoke-tested on next start
S4 | Detection engine FD-01/02/03/05/06, scoring, cases + tests | §5, §9 | 50 |  |  | Done | 2026-10-31 | b5d47e7 | 39 tests; 11/11 fraud, 7/7 lookalikes on 3 seeds; precision 79–92%; ~70 ms/run
S5 | UI part 1: Dashboard, Ingest, Alerts list + detail | §7.1–7.4 | 30 |  |  | Done | 2026-10-31 | ec2d613 | Screens checked in Playwright at 1440/390 px, light + dark; no overflow
S6 | UI part 2: Cases + decisions, Customer timeline, Rules, Evaluation | §7.5–7.8 | 30 |  |  | Done | 2026-10-31 |  | 45 tests; browser E2E: decision persists after reload; evaluation 11/11, 7/7 on seed 3
S7 | Hardening, README/limitations, deploy, demo rehearsal | §10, §11 | 20 |  |  | Not started
Total

## Tasks
ID | Sprint | Task | Done when | Status | Owner | Completed on | Commit | Notes
T0.1 | S0 | git init, first commit, push to GitHub | main exists on origin | Done |  | 2026-10-31 | first commit
T0.2 | S0 | Commit PLAN.md and SPRINTS.xlsx tracker | Both files on main | Done |  | 2026-10-31
T1.1 | S1 | create-next-app (TS, App Router, Tailwind), .gitignore | npm run build passes | Done |  | 2026-10-31
T1.2 | S1 | Drizzle + libSQL client; schema for source, bookkeeping, detection and case tables | Tables created on a fresh DB | Done |  | 2026-10-31 |  | Raw SQL via @libsql/client instead of Drizzle
T1.3 | S1 | Immutability triggers on alerts and case_decisions | UPDATE alerts aborts | Done |  | 2026-10-31
T1.4 | S1 | config/policy.json with all weights and thresholds | Loaded and typed by lib/policy.ts | Done |  | 2026-10-31
T1.5 | S1 | Utilities: normalize, hash, stats (median/MAD/p95), union-find | Unit tests pass | Done |  | 2026-10-31
T2.1 | S2 | Seeded PRNG + background population (customers, accounts, txns, logins, loans) | Deterministic output per seed | Done |  | 2026-10-31
T2.2 | S2 | Planted fraud scenarios S1–S6 | Present in ground_truth.json | Done |  | 2026-10-31
T2.3 | S2 | Planted lookalikes L1–L4 | Present in ground_truth.json | Done |  | 2026-10-31
T2.4 | S2 | Outputs: CSV ×5, XLSX, JSON, errors file, alias-header file, ground truth | Seeds 1–3 committed | Done |  | 2026-10-31
T3.1 | S3 | Parsers: CSV, XLSX (multi-sheet), JSON (array or keyed) | Same seed → same rows in all 3 formats | Done |  | 2026-10-31
T3.2 | S3 | Header aliases + dataset type detection + override | Alias file maps correctly | Done |  | 2026-10-31
T3.3 | S3 | zod row validation + value normalisation | Bad rows report field + message | Done |  | 2026-10-31 |  | Explicit field validators (clear per-field messages); zod for API bodies
T3.4 | S3 | Buckets: accepted / rejected / duplicate / warning; conflict detection | total = sum of buckets | Done |  | 2026-10-31
T3.5 | S3 | APIs: /api/ingest, /api/samples, /api/samples/load, /api/batches, errors.csv | Ingestion tests pass | Done |  | 2026-10-31
T4.1 | S4 | DetectionContext: indexes, sorted histories, baselines | Built once per run | Done |  | 2026-10-31
T4.2 | S4 | FD-01 suspicious transfer | S2–S4 detected; L2 not Medium+ | Done |  | 2026-10-31
T4.3 | S4 | FD-02 shared device | S5 device High; L1 Low | Done |  | 2026-10-31
T4.4 | S4 | FD-03 account takeover | S1 High; L3 Low; L4 none | Done |  | 2026-10-31
T4.5 | S4 | FD-05 loan application ring | S5 High | Done |  | 2026-10-31
T4.6 | S4 | Scoring, floors, fingerprints, insert-only persistence | Re-run adds 0 alerts | Done |  | 2026-10-31
T4.7 | S4 | FD-06 cross-system correlation + hub exclusion | S5+S6 in one component | Done |  | 2026-10-31
T4.8 | S4 | Case builder + /api/detect | Re-run adds 0 cases | Done |  | 2026-10-31 |  | Cases group every Medium/High alert sharing an entity; FD-06 only when a group spans ≥2 customers or products
T4.9 | S4 | Detection + integrity tests on seeds 1–3 | vitest green | Done |  | 2026-10-31
T5.1 | S5 | App shell, nav, shared UI components | All routes reachable | Done |  | 2026-10-31
T5.2 | S5 | Dashboard + /api/dashboard | Counts match DB | Done |  | 2026-10-31 |  | Charts as plain HTML bars (Recharts dropped): status colours + labels for risk, single hue for categories
T5.3 | S5 | Ingest screen: sample picker, upload, result cards, history | Bad file shows 5 issues | Done |  | 2026-10-31
T5.4 | S5 | Alerts list: tabs + 6 filters + /api/alerts | Each filter narrows results | Done |  | 2026-10-31
T5.5 | S5 | Alert detail: primary event, why-flagged table, source rows | Every evidence ref resolves | Done |  | 2026-10-31
T6.1 | S6 | Case queue + case detail + merged timeline | FD-06 case shows all members | Done |  | 2026-10-31
T6.2 | S6 | Decision form + history + revised level/category | Persists after refresh; alert unchanged | Done |  | 2026-10-31
T6.3 | S6 | Customer investigation page + timeline | Linked devices list other customers | Done |  | 2026-10-31
T6.4 | S6 | Rules page | Shows policy version + weights | Done |  | 2026-10-31
T6.5 | S6 | Evaluation page + /api/evaluate | All seed-3 scenarios pass | Done |  | 2026-10-31
T7.1 | S7 | Reset workspace + error handling pass | No stack traces reach the client | Not started
T7.2 | S7 | README + KNOWN_LIMITATIONS | Run steps work from a clean clone | Not started
T7.3 | S7 | Deploy (Vercel + Turso) | Deployed URL passes §11 | Not started
T7.4 | S7 | Demo rehearsal on seed 3 | §11 completed in ≤ 4 min | Not started

## Requirements
ID | Official requirement | Implemented by | Status | Verified on | Notes
R1 | Upload or select data from different systems | Ingest screen: upload + sample picker | Verified | 2026-10-31 | Ingest screen: sample picker + upload (screenshot-checked)
R2 | Customer/account, transaction, device/login data | customers, accounts, transactions, login_events | Verified | 2026-10-31 | tests/ingest.test.ts
R3 | CSV, Excel, JSON | lib/ingest/parse.ts | Verified | 2026-10-31 | tests/ingest.test.ts
R4 | Validate; flag missing mandatory fields; never silently ignore | Validation buckets + error report | Verified | 2026-10-31 | tests/ingest.test.ts
R5 | Common structure linked by shared IDs | Schema + application_id on disbursements | Verified | 2026-10-31 | tests/ingest.test.ts
R6 | Configurable rules + statistics | config/policy.json + Rules page | Verified | 2026-10-31 | config/policy.json rendered on /rules
R7 | Suspicious transfers | FD-01 | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R8 | Shared devices and whether suspicious | FD-02 | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R9 | Repeated login failures → success / sensitive activity | FD-03 | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R10 | Legitimate lookalikes | Mitigations + Reviewed tab + L1–L4 | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R11 | At least one extra scenario | FD-05 (+ FD-06) | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R12 | Multi-indicator risk classification | lib/detect/score.ts | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R13 | Normal high value ≠ fraud; after login risk scores higher | FD-01 WITHIN_CUSTOMER_NORM / PRECEDED_BY_LOGIN_RISK | Verified | 2026-10-31 | tests/detect.test.ts + tests/integrity.test.ts (seeds 1–3)
R14 | Explain contributing factors | Why-flagged table | Verified | 2026-10-31 | Why-flagged table with weights, details, evidence links
R15 | Dashboard metrics | Dashboard screen | Verified | 2026-10-31 | Dashboard: records, flagged, risk distribution, categories, products
R16 | Filters: customer, transaction, product, risk, date, detector | Alerts screen + /api/alerts | Verified | 2026-10-31 | All 6 filters checked against /api/alerts on seed 3
R17 | Alert shows event, reasons, supporting records | Alert detail | Verified | 2026-10-31 | Alert detail: underlying event, reasons, source rows with file:row
R18 | Case: ID, customer/account, category, risk, evidence, status | cases + case_decisions | Verified | 2026-10-31 | Case: ID, customer/account, category, risk, evidence, status (tests/cases.test.ts)
R19 | Record a decision | Case decision form | Verified | 2026-10-31 | Decision form; persisted across reload in browser E2E
R20 | Preserve original alert after reclassification | Insert-only alerts + trigger | Verified | 2026-10-31 | Alerts byte-identical after decision + reclassification (tests/cases.test.ts)